## Lookups
Category | Risk_Status | Control_Strength | Buisness_Unit | Action Status | Priority | Risk_Source
Operational | Risk_Status | Weak | GO Ops | Not Started | Low | Workshop
IT | New | Moderate | Bus Ops | In Progress | Medium | Ops Meeting
Safety | In Review | Strong | Capital Projects | Done | High | Audit
Finance | Active |  | Corp Services | Blocked | Critical | Incident
Projects | Closed |  | Customer Experience
Reputation |  |  | Stations/Facillities
Office of CRO

## Risk_Register
Risk_ID | Title | Category | Buisness_Unit | Owner | Date_Identified | Status | Likelihood_Inherent | Impact_Inherent | Score_Inherent | Control_Strength | Likelihood_Residual | Impact_residual | Score_residual | Appetite_alignment | Last_review_date | Next_review_date | Days_Open | Is_Overdue_review | Risk_Source | Key_Controls | MItigation_Summary
RSK-2025-0001 | Service Disruption due to Weather | Operational | Bus Ops | Customer Communications Manager | 2025-11-25 | Closed | 4 | 2 | 8 | Weak | 4 | 1 | 4 | Within | 2025-11-27 | 2025-12-02 | 2 | FALSE | Ops Meeting | Weather monitoring; service recovery procedures | Improve severe weather response and ensure adequate resource coverage during storms.
RSK-2025-0002 | Cybersecurity Vulnerabilities | IT | Corp Services | Cybersecurity Manager | 2025-11-25 | Closed | 3 | 5 | 15 | Strong | 2 | 2 | 4 | Within | 2025-11-28 | 2025-12-02 | 3 | FALSE | Audit | MFA; vulnerability scanning; security monitoring | Address critical vulnerabilities and strengthen security monitoring and evaluate management timelines.
RSK-2025-0003 | Equipment failure limits facility accessibility | Reputation | Customer Experience | Accessibility Program Manager | 2025-11-26 | Closed | 1 | 4 | 4 | Moderate | 3 | 2 | 6 | Within | 2025-12-05 | 2025-12-03 | 9 | FALSE | Incident | Preventative maintenance; vendor escalation process | Prioritize accessibility equipment repairs and improve vendor response time tracking.
RSK-2025-0004 | Service Disruption due to Weather | Operational | Stations/Facillities | Supervisor, Stations & Facilities | 2025-11-28 | Closed | 4 | 2 | 8 | Weak | 1 | 1 | 1 | Within | 2025-12-02 | 2025-12-05 | 4 | FALSE | Ops Meeting | Winter maintenance; incident response procedures | Strengthen winter readiness and ensure station teams follow standardized disruption protocols.
RSK-2025-0005 | Slip hazard due to Winter Condition | Safety | Stations/Facillities | Stations Maintenance Lead | 2025-11-28 | Closed | 3 | 3 | 9 | Weak | 1 | 1 | 1 | Within | 2025-12-02 | 2025-12-02 | 4 | FALSE | Incident | Salt/grit procedures; safety inspections | Increase winter inspections and standardize hazard reporting and follow-up.
RSK-2025-0006 | Maintenance Request Delay | Operational | Stations/Facillities | Supervisor, Stations & Facilities | 2025-12-01 | Closed | 3 | 3 | 9 | Moderate | 2 | 2 | 4 | Within | 2025-12-04 | 2025-12-04 | 3 | FALSE | Staff Report | Work order process; triage procedures | Prioritize work orders more effectively and monitor maintenance request response time KPIs.
RSK-2025-0007 | Systems Integration Delays Resulting in Duplicate Requests | IT | Corp Services | IT Operations Lead | 2025-12-02 | Closed | 2 | 2 | 4 | Moderate | 1 | 1 | 1 | Within | 2025-12-09 | 2025-12-09 | 7 | FALSE | Project Review | Change management; system testing procedures | Enhance integration testing and put restrictions in place to cut down on the number of duplicate requests.
RSK-2026-0008 | Stakeholder Dissatisfaction Following Project Delays | Finance | Office of CRO | Senior Manager, Risk Advisory | 2026-02-12 | In Review | 2 | 5 | 10 | Moderate | 4 | 4 | 16 | Outside | 2026-02-12 | 2026-02-19 | 0 | FALSE | Project Review | Project governance; schedule oversight | Improve stakeholder communications and implement escalation triggers for project delay impacts.
RSK-2025-0009 | Service Delays leading to Customer Dissatisfaction | Reputation | Customer Experience | Customer Communications Manager | 2025-12-05 | Closed | 3 | 3 | 9 | Weak | 1 | 1 | 1 | Within | 2025-12-12 | 2025-12-12 | 7 | FALSE | Ops Meeting | Service alerts; operational recovery protocols | Improve disruption communications and improve consistency of service recovery.
RSK-2026-0010 | Scope Creep leads to Stakeholder Concern | Finance | Office of CRO | Senior Manager, Risk Advisory | 2026-01-07 | In Review | 3 | 5 | 15 | Moderate | 4 | 3 | 12 | Borderline | 2026-02-11 | 2026-02-18 | 35 | FALSE | Project Review | Stakeholder governance; change control process | Improve scope management and ensure stakeholder alignment through standardized change control.
RSK-2025-0011 | Equipment Failure causes Service Disruptions | Safety | Stations/Facillities | Safety Program Lead | 2025-12-11 | Closed | 2 | 4 | 8 | Moderate | 3 | 2 | 6 | Within | 2025-12-18 | 2025-12-18 | 7 | FALSE | Incident | Preventative maintenance; safety checks | Reduce equipment failures through enhanced preventative maintenance tracking and recurring issue analysis.
RSK-2026-0012 | Data Access Issues Following Staff Turnover | IT | Corp Services | IT Operations Lead | 2026-02-09 | In Review | 2 | 4 | 8 | Strong | 2 | 3 | 6 | Within | 2026-02-09 | 2026-02-16 | 0 | FALSE | Incident | Access management process; onboarding/offboarding controls | Improve access provisioning controls and ensure timely access removal following staff turnover.
RSK-2026-0013 | Customer Dissatisfaction following Maintenance Delays | Reputation | GO Ops | Customer Communications Manager | 2025-12-31 | Closed | 2 | 3 | 6 | Weak | 1 | 1 | 1 | Within | 2026-01-07 | 2026-01-07 | 7 | FALSE | Staff Report | Maintenance triage; customer communications process | Improve maintenance scheduling transparency and strengthen customer-facing updates.
RSK-2026-0014 | Trip Hazard due to facility Upgrades | Safety | Stations/Facillities | Safety Program Lead | 2026-01-01 | Closed | 1 | 4 | 4 | Strong | 4 | 1 | 4 | Within | 2026-01-08 | 2026-01-08 | 7 | FALSE | Incident | Safety signage; work zone procedures | Strengthen work zone safety controls and ensure consistent signage and hazard checks.
RSK-2026-0015 | Communications Delays leading to Customer Dissatisfaction | Reputation | Customer Experience | Customer Communications Manager | 2026-01-05 | Closed | 2 | 2 | 4 | Strong | 1 | 1 | 1 | Within | 2026-01-12 | 2026-01-12 | 7 | FALSE | Ops Meeting | Alert protocols; escalation procedures | Improve timeliness of customer communications during disruptions through clearer escalation roles.
RSK-2025-0016 | Budget constraints effecting LRT timeline | Finance | Office of CRO | Senior Manager, Risk Advisory | 2025-12-02 | Active | 1 | 3 | 3 | Moderate | 2 | 2 | 4 | Within | 2026-02-09 | 2025-12-16 | 69 | TRUE | Project Review | Budget oversight; governance approvals | Strengthen cost forecasting and implement early escalation for budget variance risks.
RSK-2026-0017 | Media Scrutiny Following Equipment Failure | Reputation | Customer Experience | Customer Communications Manager | 2026-01-09 | Closed | 4 | 5 | 20 | Strong | 4 | 2 | 8 | Within | 2026-01-16 | 2026-01-16 | 7 | FALSE | Incident | Incident communications protocol; issue escalation | Improve communications preparation and ensure consistent messaging following service disruptions.
RSK-2026-0018 | System Downtime leading to Delayed App Communications | IT | Corp Services | IT Operations Lead | 2026-01-12 | Closed | 3 | 2 | 6 | Strong | 3 | 1 | 3 | Within | 2026-01-19 | 2026-01-19 | 7 | FALSE | Incident | System monitoring; incident response procedures | Improve system uptime through proactive monitoring and standardized incident response escalation.
RSK-2026-0019 | Budget Constraints Limiting Planned Facility Upgrades | Finance | Office of CRO | Senior Manager, Risk Advisory | 2026-01-12 | Closed | 2 | 3 | 6 | Moderate | 1 | 2 | 2 | Within | 2026-01-19 | 2026-01-19 | 7 | FALSE | Project Review | Budget monitoring; variance reporting | Improve cost tracking and implement early escalation for budget risks impacting facility upgrades.
RSK-2026-0020 | Station Closure due to Electrical Hazard | Operational | Stations/Facillities | Supervisor, Stations & Facilities | 2026-01-14 | Closed | 5 | 5 | 25 | Weak | 2 | 2 | 4 | Within | 2026-01-21 | 2026-01-21 | 7 | FALSE | Incident | Electrical inspections; safety response procedures | Reduce likelihood of electrical hazards through preventative inspections and response readiness.
RSK-2025-0021 | Construction Delays impacting Accessibility Projects | Projects | Capital Projects | Accessibility Program Manager | 2025-12-09 | Active | 2 | 4 | 8 | Weak | 2 | 2 | 4 | Within | 2025-12-16 | 2026-02-23 | 7 | FALSE | Project Review | Project schedules; contractor oversight | Improve contractor performance tracking and implement escalation triggers for potential slippage.
RSK-2025-0022 | Delays in Project Progression due to insufficient Documentation | Projects | Capital Projects | Project Controls Manager | 2025-12-29 | Active | 2 | 3 | 6 | Strong | 1 | 2 | 2 | Within | 2026-02-09 | 2026-02-16 | 42 | FALSE | Audit | Documentation standards; project governance reviews | Standardize documentation templates and enforce tighter deadlines.
RSK-2026-0023 | Customer Dissatisfaction due to Station Uncleanliness | Reputation | Stations/Facillities | Supervisor, Stations & Facilities | 2026-01-21 | Active | 2 | 1 | 2 | Strong | 2 | 1 | 2 | Within | 2026-02-11 | 2026-02-18 | 21 | FALSE | Ops Meeting | Cleaning schedules; quality inspections | Improve station cleanliness tracking and implement service-level reporting for recurring issues.
RSK-2026-0024 | CCTV Outages Limiting Incident Response Capability | Safety | Stations/Facillities | Supervisor, Stations & Facilities | 2026-01-27 | New | 2 | 4 | 8 | Moderate | 1 | 2 | 2 | Within | 2026-02-10 | 2026-02-17 | 14 | FALSE | Audit | CCTV monitoring; access controls | Improve CCTV uptime and establish escalation for outages impacting incident response.
RSK-2026-0025 | Emergency Drill Inconsistency Across Sites | Safety | Stations/Facillities | Supervisor, Stations & Facilities | 2026-02-05 | New | 1 | 4 | 4 | Strong | 1 | 2 | 2 | Within | 2026-02-12 | 2026-02-19 | 7 | FALSE | Staff Report | Emergency preparedness program; compliance tracking | Standardize emergency drill scheduling and track completion across sites.
RSK-2026-0026 | Public Dissatisfaction Following Station Closure | Reputation | Customer Experience | Customer Communications Manager | 2026-01-15 | In Review | 3 | 2 | 6 | Weak | 1 | 1 | 1 | Within | 2026-02-12 | 2026-02-19 | 28 | FALSE | Staff Report | Customer communication standards; issue escalation | Improve customer communications during station disruptions through standardized messaging and timelines.
RSK-2026-0027 | Trespassing Incident | Safety | GO Ops | Safety Program Lead | 2026-01-19 | In Review | 1 | 4 | 4 | Weak | 1 | 1 | 1 | Within | 2026-02-13 | 2026-02-16 | 25 | FALSE | Incident | Safety patrols; incident reporting procedures | Strengthen trespassing prevention and improve reporting consistency for follow-up.
Formulas:
Is_Overdue_review = AND(tblRisks[[#This Row],[Status]]<>"Closed",tblRisks[[#This Row],[Next_review_date]]<TODAY())

## Action_Tracker
Action_ID | Risk_ID | Action_Title | Owner | Due_Date | Status | Priority | Percent_Complete | Is_Overdue | Days_Overdue | Last_Updated | Notes
ACT-2025-0001 | RSK-2025-0001 | Service Disruption due to Weather | Customer Communications Manager | 2025-12-02 | Closed | Low | 100% | FALSE
ACT-2025-0002 | RSK-2025-0002 | Cybersecurity Vulnerabilities | Cybersecurity Manager | 2025-12-02 | Closed | High | 100% | FALSE
ACT-2025-0003 | RSK-2025-0003 | Equipment failure limits facility accessibility | Accessibility Program Manager | 2025-12-03 | Closed | High | 100% | FALSE
ACT-2025-0004 | RSK-2025-0004 | Service Disruption due to Weather | Supervisor, Stations & Facilities | 2025-12-05 | Closed | Low | 100% | FALSE
ACT-2025-0005 | RSK-2025-0005 | Slip hazard due to Winter Condition | Stations Maintenance Lead | 2025-12-02 | Closed | Medium | 100% | FALSE
ACT-2025-0006 | RSK-2025-0006 | Maintenance Request Delay | Supervisor, Stations & Facilities | 2025-12-04 | Closed | Medium | 100% | FALSE
ACT-2025-0007 | RSK-2025-0007 | Systems Integration Delays Resulting in Duplicate Requests | IT Operations Lead | 2025-12-09 | Closed | Low | 100% | FALSE
ACT-2026-0008 | RSK-2026-0008 | Budget constraints effecting LRT timeline | Senior Manager, Risk Advisory | 2026-02-19 | Active | High | 75% | FALSE | 0
ACT-2025-0009 | RSK-2025-0009 | Service Delays leading to Customer Dissatisfaction | Customer Communications Manager | 2025-12-12 | Closed | Low | 100% | FALSE
ACT-2026-0010 | RSK-2026-0010 | Construction Delays impacting Accessibility Projects | Accessibility Program Manager | 2026-02-18 | In Review | High | 50% | FALSE | 0
ACT-2025-0011 | RSK-2025-0011 | Equipment Failure causes Service Disruptions | Safety Program Lead | 2025-12-18 | Closed | High | 100% | FALSE
ACT-2026-0012 | RSK-2026-0012 | Delays in Project Progression due to insufficient Documentation | Project Controls Manager | 2026-02-16 | Active | High | 75% | FALSE | 0
ACT-2026-0013 | RSK-2026-0013 | Customer Dissatisfaction following Maintenance Delays | Customer Communications Manager | 2026-01-07 | Closed | Low | 100% | FALSE
ACT-2026-0014 | RSK-2026-0014 | Trip Hazard due to facility Upgrades | Safety Program Lead | 2026-01-08 | Closed | Medium | 100% | FALSE
ACT-2026-0015 | RSK-2026-0015 | Communications Delays leading to Customer Dissatisfaction | Customer Communications Manager | 2026-01-12 | Closed | Low | 100% | FALSE
ACT-2025-0016 | RSK-2026-0016 | Scope Creep leads to Stakeholder Concern | Senior Manager, Risk Advisory |  | In Review | Critical | 50% | FALSE |  | 2026-02-13 | CRO meeting scheduled
ACT-2026-0017 | RSK-2026-0017 | Media Scrutiny Following Equipment Failure | Customer Communications Manager | 2026-01-16 | Closed | High | 100% | FALSE
ACT-2026-0018 | RSK-2026-0018 | System Downtime leading to Delayed App Communications | IT Operations Lead | 2026-01-19 | Closed | Low | 100% | FALSE
ACT-2026-0019 | RSK-2026-0019 | Budget Constraints Limiting Planned Facility Upgrades | Senior Manager, Risk Advisory | 2026-01-19 | Closed | Low | 100% | FALSE
ACT-2026-0020 | RSK-2026-0020 | Station Closure due to Electrical Hazard | Supervisor, Stations & Facilities | 2026-01-21 | Closed | Low | 100% | FALSE
ACT-2025-0021 | RSK-2026-0021 | Public Dissatisfaction Following Station Closure | Customer Communications Manager |  | In Review | Low | 25% | FALSE |  | 2026-02-13
ACT-2025-0022 | RSK-2026-0022 | Trespassing Incident | Safety Program Lead |  | In Review | Medium | 25% | FALSE |  | 2026-02-13
ACT-2026-0023 | RSK-2026-0023 | Customer Dissatisfaction due to Station Uncleanliness | Supervisor, Stations & Facilities | 2026-02-18 | Active | Low | 75% | FALSE | 0 | 2026-02-13
ACT-2026-0024 | RSK-2026-0024 | CCTV Outages Limiting Incident Response Capability | Supervisor, Stations & Facilities | 2026-02-17 | New | High | 0% | FALSE | 0
ACT-2026-0025 | RSK-2026-0025 | Emergency Drill Inconsistency Across Sites | Supervisor, Stations & Facilities | 2026-02-19 | New | High | 0% | FALSE | 0
ACT-2026-0026 | RSK-2026-0026 | Data Access Issues Following Staff Turnover | IT Operations Lead | 2026-02-19 | In Review | High | 25% | FALSE | 0 | 2026-02-13
ACT-2026-0027 | RSK-2026-0027 | Stakeholder Dissatisfaction Following Project Delays | Senior Manager, Risk Advisory | 2026-02-16 | In Review | Critical | 25% | FALSE | 0 | 2026-02-13
ACT-2026-0101 | RSK-2026-0008 | Create revised cost forecast and identify top 3 funding gaps | Senior Manager, Risk Advisory | 2026-01-15 | Active | High | 0% | TRUE | 32 | 2026-01-15 | Initial draft started, awaiting finance inputs
ACT-2026-0102 | RSK-2026-0010 | Confirm revised construction schedule and update comms plan | Accessibility Program Manager | 2026-02-01 | Active | Medium | 25% | TRUE | 15 | 2026-02-01 | Waiting on contractor confirmation
ACT-2026-0103 | RSK-2026-0012 | Create documentation checklist and assign missing deliverables | Project Controls Manager | 2026-01-20 | Active | High | 10% | TRUE | 27 | 2026-01-20
ACT-2026-0104 | RSK-2026-0016 | Run scope review workshop and log decisions in tracker | Senior Manager, Risk Advisory | 2026-02-05 | In Review | High | 40% | TRUE | 10 | 2026-02-05 | Workshop scheduled, agenda created
ACT-2026-0105 | RSK-2026-0021 | Draft public response template for closures and delays | Customer Communications Manager | 2026-02-10 | Active | Medium | 50% | TRUE | 5 | 2026-02-10 | Template drafted, pending review
ACT-2026-0106 | RSK-2026-0022 | Coordinate site walk-through and update safety signage checklist | Safety Program Lead | 2026-02-06 | Active | High | 20% | TRUE | 9 | 2026-02-06 | Walk-through booked with ops
ACT-2026-0107 | RSK-2026-0023 | Implement cleaning tracking log and weekly audit process | Supervisor, Stations & Facilities | 2026-02-12 | Active | Low | 0% | TRUE | 3 | 2026-02-12 | Audit template created
ACT-2026-0108 | RSK-2026-0027 | Prepare stakeholder update deck and mitigation timeline | Senior Manager, Risk Advisory | 2026-02-13 | Active | Medium | 15% | TRUE | 2 | 2026-02-13 | Outline created, needs metrics
Formulas:
Due_Date = IFERROR(VLOOKUP(tblActions[[#This Row],[Risk_ID]], tblRisks[], MATCH("Next_review_date", tblRisks[#Headers], 0), FALSE), "")
Is_Overdue = IF(tblActions[[#This Row],[Status]]="Closed",FALSE,IF(tblActions[[#This Row],[Due_Date]]="",FALSE,tblActions[[#This Row],[Due_Date]]<TODAY()))
Days_Overdue = IF(tblActions[[#This Row],[Status]]="Closed","",IF(tblActions[[#This Row],[Due_Date]]="","",MAX(0,TODAY()-tblActions[[#This Row],[Due_Date]])))

## Dashboard
Enterprise Risk Dashboard |  | (Simulated Data)
| Filter: Status |  | KPI Summary
|  | Total Risks | Active Risks | Outside Risk Appetite
|  | 27 | 4 | 1
|  | Open Actions | Overdue Reviews | Overdue Actions
|  | 19 | 1 | 8
Top Ten Risks
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Pivot_Data
Pivot Tables |  |  |  |  | KPI's
| Category | Count | Business Unit | Count |  | 1 | Total Risks | 27
| Finance | 4 | Bus Ops | 1 |  | 2 | Active Risks | 4
| IT | 4 | Capital Projects | 2 |  | 3 | Outside Apetite | 1
| Operational | 4 | Customer Experience | 5 |  | 4 | Open Actions | 19
| Projects | 2 | GO Ops | 2 |  | 5 | Overdue Reviews | 1
| Reputation | 7 | Office of CRO | 4 |  | 6 | Overdue Actions | 8
| Safety | 6 | Grand Total | 14
| Grand Total | 27